## Instructions
The provided checklist is designed to assist the user with general installation guidance and pre-inspection quality control.
Refer to manufacturer's installation instructions for product specific information which may supercede the information given here.
See DrJ Best Practices for additional Educational Programs

## Checklist
Revised 2/15/2017
Items to be Checked | Installer | Building Official | Comments
The following should be verified when using the installation method described on DrJ Best Practices:
On the ground, ensure level bearing before setting first five trusses
Plumb and properly brace the trusses to the ground.
Add lumber spacer pieces to top chord:
Spacers are at least 27" long
Spacers are attached to top chord every six feet to hold trusses plumb and properly spaced.
Spacers are attached with two 16d box nails.
Hoist all trusses using spreader bar to keep trusses rigid
Sheathing
Sheathing is installed alternating 4x8 and 4x4 sheets from heel up to truss peak.
Sheathing is installed in the alternating gaps so that two feet extends past the sixth truss.
Sheathing is fastened to trusses per construction documents.
Required Bottom Chord Bracing:
Permanent lateral bracing is installed every ten feet
Permanent diagonal bracing is installed